## Slide 1: Development plan and Project Cycle Management

## Slide 2: .
WHAT?
HOW?
WHY?
Simon Sinek “How great leaders inspire action”
https://www.youtube.com/watch?v=qp0HIF3SfI4
Start with why
Notes: Explain the Golden Circle.

## Slide 3
Why?
How?
What?
Where?
Who?
When?
How Much?
WHAT THEN??
The Plan – ask yourself…

## Slide 4
Start with your WHY, and identify the Topic
  The Rationale will come from your Country/Issue Report
Analyse!
  The Situation
  The People (stakeholder Analysis) Who has an interest/stake?
Expand the Problem and find the Solution/s:
  Problem/Solution Tree
HOW? The Strategy:
  Choose your battles
  Develop your plan
Formalise the WHAT! The Logical sequence of things:
  Overall Goal – The Big Why - IMPACT
  Specific Objective – Overall Outcome – your contribution to the Big Why
  Results – Contributes to Outcome
  Outputs - Activities > Timeline > Budget!!
Developing your Course Work - DP

## Slide 5
Remember: LESS is MORE – max. 4000 words….!
SHORT Analysis/Problem statement (From Country report)
The Body: follow your logical sequence – you may add a SWOT and a Stakeholder Analysis matrix.
Logframe will also help…
Activities – be clear, be simple, be specific.
Timeline and Budget – summary.
Sustainability?
Basic Structure

## Slide 6
Use logframes (logical frameworks) to provide details.
S = Specific; actually show impact and change
M = Measurable; quantitative metrics or clear qualitative indicators
A = Achievable; realistic goals (better to under-promise and over-deliver?)
R = Relevant; stay within scope of the projects fund allocation
T = Time-bound; year-by-year, and project-end targets
Being SMART
Notes: Show VN logframe